## Module Picks
Campus Connect: Module Picks
How to fill in: type your name in a yellow header cell (row 11), then in your column pick "Lead" or "Interested" from the dropdown for any module. Leave it empty if you're not interested. The Lead fills the Owner column (yellow, right) at the team meeting.
Example: in the Posts row, someone who wants to lead it picks Lead in their column; someone who would help picks Interested. Blue numbers and yellow cells are inputs the team can change.
People sharing the work | 7 |  | Hours per week per person | 10
Learning overhead (juniors) | 75% |  | Weeks (Winter term) | 13
Reliability overhead | 50% |  | Available dev-days per person
Total estimated work (dev-days) |  |  | Does the plan fit?
Fair share per person (dev-days)
Section | Module | Base days (API integration) | Est. days (junior + reliable) | Uses (API / library) | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | # Lead | # Interested | Wants to lead | Owner | Status
Shared layers and infrastructure | Testing and CI | 3 |  | JUnit, Jest, GitHub Actions
Shared layers and infrastructure | Performance / load testing | 2 |  | k6
Shared layers and infrastructure | Cache layer (Yantian is leading) | 2 |  | Spring Cache + Caffeine / Redis
Shared layers and infrastructure | Message queue (MQ) layer | 4 |  | Kafka or RabbitMQ
Shared layers and infrastructure | Database design (tables and schema) | 3 |  | MySQL
Shared layers and infrastructure | Database migrations | 1 |  | Flyway
Shared layers and infrastructure | Index tuning and query performance | 1 |  | MySQL indexes, EXPLAIN
Shared layers and infrastructure | RPC / service contracts | 4 |  | REST + OpenAPI between services
Shared layers and infrastructure | Deployment / DevOps | 4 |  | AWS EC2 + RDS, Docker
Shared layers and infrastructure | Logging and monitoring | 1 |  | Sentry
Shared layers and infrastructure | Security and rate limiting | 2 |  | Spring Security, Bucket4j
Shared layers and infrastructure | Backup | 0.5 |  | RDS automatic backups
Shared layers and infrastructure | App updates | 0.5 |  | Expo EAS Update
Shared layers and infrastructure | Offline storage | 3 |  | expo-sqlite
Accounts and settings | Sign-in and accounts | 3 |  | Spring Security + JWT
Accounts and settings | Authorization / permissions | 2 |  | Spring Security roles
Accounts and settings | Email verification | 1 |  | Email API (SES / SendGrid)
Accounts and settings | User profiles | 2 |  | Spring Boot + MySQL
Accounts and settings | QR code profile sharing | 0.5 |  | react-native-qrcode-svg
Accounts and settings | Settings | 1 |  | Expo + REST
Accounts and settings | French language support | 2 |  | i18next + translation
Accounts and settings | Import / export | 1 |  | JSON / CSV
Social | Follows | 1.5 |  | Spring Boot + MySQL
Social | Posts | 3 |  | Spring Boot + MySQL, cursor pagination
Social | Comments | 1.5 |  | Spring Boot + MySQL
Social | Likes | 1 |  | Spring Boot + MySQL
Social | Mentions | 1
Social | Course tags | 1
Social | Industry / research tags | 1
Social | Verified alumni / industry badge | 2 |  | Manual review flow
Social | Saved posts | 1
Social | Image upload | 1.5 |  | AWS S3 presigned URLs
Social | Search | 2 |  | MySQL FULLTEXT
Safety | Moderation / admin | 2.5 |  | Report queue + admin screen
Safety | Block and mute users | 1
Safety | Feedback / ticketing | 0.5 |  | Sentry user feedback
Messaging and notifications | Instant messaging | 5 |  | WebSocket (Spring STOMP)
Messaging and notifications | Chat attachments | 1 |  | AWS S3
Messaging and notifications | Chat search | 1 |  | MySQL FULLTEXT
Messaging and notifications | In-app notifications | 2 |  | Spring Boot + WebSocket
Messaging and notifications | Push notifications | 1 |  | Expo Push
Messaging and notifications | SMS | 0.5 |  | Twilio
Messaging and notifications | Email | 0.5 |  | SendGrid or AWS SES
Tools | Seat Alert | 5 |  | No official API: scraping or McGill IT approval
Tools | Course catalog data | 2 |  | McGill eCalendar (no official API)
Tools | Course Averages | 3 |  | Student-submitted data
Tools | Campus map | 1 |  | react-native-maps
Tools | McGill links redirection | 0.5 |  | expo-web-browser
Other | UI | 8 |  | Expo Router + React Native Paper
Other | Payment system | 1.5 |  | Stripe Payment Links
Workload per person (dev-days)
Wants to lead (days)
Interested (days)
Assigned as Owner (days)
Fair share (days)
Owner days minus fair share
Red = more than 5 days over the fair share; orange = more than 5 days under. Assigned total for the team:
Note on B5: Split assumed equal across 7 people, as requested by the Lead.
Note on E5: Assumption: 10 h/week each. 1 dev-day = 8 hours.
Note on B6: Extra time to learn each tool well enough to explain what happens: docs, tutorials, small experiments. Juniors: 50-100%.
Note on B7: Extra time for tests, error handling, edge cases, code review and docs, so the feature is reliable, not just working once.
Note on C11: Time for an experienced developer to build the module from scratch (no starter code), using the API or library in column E. Column D adds the learning and reliability overheads (B6, B7).